## Sheet1
MEIS-ALERT INTRUSION DETECTION SYSTEM PROJECT
DETAILED GANTT CHART
CLAUDIO F. MEIS - N00674230
2019-09-12
TASK NAME |  | DURATION (DAYS) | START DATE | FINISH DATE | OWNER | SEPTEMBER | [24 empty] | OCTOBER | [30 empty] | NOVEMBER
[6 empty] | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 31 | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13
Initiating Phase |  | 8 | 2019-09-06 | 2019-09-13 | bar: SEPTEMBER 6 to SEPTEMBER 14
| Identify Objectives | 3 | 2019-09-06 | 2019-09-08 | Claudio | bar: SEPTEMBER 6 to SEPTEMBER 8
| Determine Project Feasibility | 2 | 2019-09-09 | 2019-09-10 | Claudio | bar: SEPTEMBER 9
| Determine Scope | 3 | 2019-09-11 | 2019-09-14 | Claudio | bar: SEPTEMBER 11 to SEPTEMBER 14
Planning Phase |  | 21 | 2019-09-15 | 2019-10-05 | bar: SEPTEMBER 15
| Create Project Plan | 6 | 2019-09-15 | 2019-09-20 | Claudio | bar: SEPTEMBER 15 to SEPTEMBER 20
| Identify Resources | 5 | 2019-09-21 | 2019-09-25 | Claudio | bar: SEPTEMBER 21 to SEPTEMBER 25
| Finalize Budget | 5 | 2019-09-26 | 2019-09-30 | Claudio | bar: SEPTEMBER 26 to SEPTEMBER 30
| Research Design | 5 | 2019-10-01 | 2019-10-05 | Claudio | bar: OCTOBER 1 to OCTOBER 5
Execution Phase |  | 34 | 2019-10-06 | 2019-11-07 | bar: OCTOBER 6
| Create Prototype Board | 5 | 2019-10-06 | 2019-10-10 | Claudio | bar: OCTOBER 6 to OCTOBER 10
| Finalize Protoype | 3 | 2019-10-11 | 2019-10-12 | Claudio | bar: OCTOBER 11 to OCTOBER 12
| Create PCB Board | 6 | 2019-10-13 | 2019-10-18 | Claudio | bar: OCTOBER 13 to OCTOBER 18
| Write Code | 8 | 2019-10-19 | 2019-10-26 | Claudio | bar: OCTOBER 19 to OCTOBER 26
| Complete Testing | 6 | 2019-10-27 | 2019-11-01 | Claudio | bar: OCTOBER 27 to NOVEMBER 1
| Fix Issues | 6 | 2019-11-02 | 2019-11-07 | Claudio | bar: NOVEMBER 2 to NOVEMBER 7
Deploy Phase |  | 6 | 2019-11-08 | 2019-11-13
| Analyze Project Performance | 6 | 2019-11-08 | 2019-11-13 | Claudio | bar: NOVEMBER 8 to NOVEMBER 13
Formulas:
START DATE = [START DATE, row above]
START DATE = [FINISH DATE, row above]+1
FINISH DATE = [START DATE]+7
FINISH DATE = [START DATE, row above]+2